## Sheet1
Task | Category | FR Code | Priority | Criticality | Time/Effort Estimation
Component Diagram | Design | N/A | 1 | N/A | 3 days
First Draft (Initial) ORM Diagrams | Design | N/A | 2 | N/A | 5 hours
Add uniform formatting to documents | Documentation | N/A | 3 | N/A | 1 hour
Use-Case Diagram | Design | N/A | 4 | N/A | 2 hours
Research Solr for search | Research | N/A | 5 | N/A | 2 days
Research SignalR for real-time message and notifications | Research | N/A | 6 | N/A | 2 days
Research testing plan ideas for small scrum projects | Research | N/A | 7 | N/A | 1 day
Write Solr Report | Documentation | N/A | 8 | N/A | 4 hours
Write Test Plan | Documentation | N/A | 9 | N/A | ?
Deployment Diagram | Design | N/A | 10 | N/A | 2 hours
User can edit owned message | Code | M-FR7 |  | Critical | TBE
Message Entiy Content (From DB tables) | Code | M-FR1 | 1 | Critical | TBE
Admin can delete any message | Code | M-FR8 |  | Critical | TBE
Module staff can delete any message belonging to one of their modules | Code | M-FR8 |  | Critical | TBE
Deleted messages are marked as deleted in database | Code | M-FR8 |  | Critical | TBE
‘Deleted’ messages are not shown to users | Code | M-FR8 |  | Critical | TBE
Referring to other users in messages | Code | M-FR2 |  | High | TBE
Order messages inside a group by time created | Code | M-FR3 |  | Medium | TBE
Order replies by time created | Code | M-FR6 |  | Medium | TBE
Students can delete an owned message if it has zero replies | Code | M-FR8 |  | High | TBE
Alert to other users when message is edited | Code | M-FR7 |  | z Low | TBE
Attach emoticons to Messages | Code | M-FR1 |  | z Low | TBE
Deploy Message Store | Testing & Deployment | N/A |  | Critical | TBE
Test Message Store API | Testing & Deployment | N/A |  | Critical | TBE
Basic Module Entity/Content |  | MR-FR1 | 1 | Critical | TBE
Admin users can create modules |  | MR-FR1 | 2 | Critical | TBE
Admin users can edit modules |  | MR-FR2 | 3 | Critical | TBE
Module has associated staff list |  | MR-FR1 | 5 | Critical | TBE
Module has associated student list |  | MR-FR3 | 4 | Critical | TBE
Module student list can be overwritten by uploaded CSV file |  | MR-FR3 |  | Critical | TBE
Restful Service from module registration – get modules by providing user and academic year |  | MR-FR4 |  | Critical | TBE
Authentication via server file for testing |  | AA-FR1 | 1 | Critical | TBE
Distinguish staff and student users by parsing return of Auth query |  | AA-FR2 | 2 | Critical | TBE
Authentication via LDAP |  | AA-FR1 | 3 | Critical | TBE
New message indicator for groups |  | M-FR9 |  | High | TBE
New message indicator for modules |  | M-FR9 |  | High | TBE
One-to-one messaging |  | M-FR5 |  | Medium | TBE
Announcement in ‘main group’ upon new group creation |  | M-FR4 |  | z Low | TBE
UI Template & CSS design coding |  | EIR-1 |  | Critical | TBE
Replying to Message in group |  | M-FR6 |  | Critical | TBE
Group Messages by group |  | M-FR3 | 10 | Critical | TBE
Make group available to all users on the module the group belongs to |  | M-FR4 | 12 | Critical | TBE
Group groups by module |  | M-FR3 | 11 | Critical | TBE
Any user can create a new group |  | M-FR4 | 8 | Critical | TBE
Display list of groups for given module |  | M-FR4 | 9 | Critical | TBE
Internationalisation of web app |  | EIR-2 | 1 | High | TBE
Welsh language localisation |  | EIR-2 | 2 | High | TBE
A user can register for notifications |  | N-FR1 |  | High | TBE
A user can change notification registration |  | N-FR1 |  | High | TBE
Daily Summary Notifications |  | N-FR2 |  | Medium | TBE
Mention Notifications |  | N-FR2 |  | Medium | TBE
Reply Notifications |  | N-FR2 |  | Medium | TBE
Notifications sent at set time intervals |  | N-FR3 |  | Medium | TBE
Search for message by text. (Search is limited to within users’ modules) |  | S-FR1 |  | Medium | TBE
Add search filter within a specific module |  | S-FR2 |  | Medium | TBE
Add search filter within a specific group |  | S-FR2 |  | Medium | TBE
Add search filter within a specific academic year |  | S-FR2 |  | Medium | TBE
No search filter/All modules a user is associated with |  | S-FR2 |  | Medium | TBE
Search returns messages that match search text |  | S-FR3 |  | Medium | TBE
If search returns message of type reply the message should be expandable to show all messages in the chain of communication (both previous and future replies) |  | S-FR3 |  | Z Low | TBE