## Sheet1
Sprint 1 - 22/10/2019
Task | Developer | Functional Requirement | Time Estimation
Research Solr for search | Morgan & Dominic (Exception for initial research) | N/A | 2 days
Component Diagram | Dominic | N/A | 3 days
First Draft (Initial) ORM Diagrams | Morgan | N/A | 5 hours
Research SignalR for real-time message and notifications | Morgan & Dominic (Exception for initial research) | N/A | 2 days
Research testing plan ideas for small scrum projects | Morgan | N/A | 1 day
Add uniform formatting to documents | Morgan | N/A | 1 hour