## Sheet1
Sprint 1 - 22/10/2019
Task | Developer | Functional Requirement | Time Estimation | Relative Importance
Research Solr for search | Morgan & Dominic (Exception for initial research) | N/A | 2 days | **
Component Diagram | Dominic | N/A | 3 days | ***** | Completed
First Draft (Initial) ORM Diagrams | Morgan | N/A | 5 hours | **** | Not done at all
Research SignalR for real-time message and notifications | Morgan & Dominic (Exception for initial research) | N/A | 2 days | ** | Some progress made
Research testing plan ideas for small scrum projects | Morgan | N/A | 1 day | * | Mostly Complete
Add uniform formatting to documents | Morgan | N/A | 1 hour | ***
Sprint 2 - 29/10/2019
Task | Developer | Functional Requirement | Time Estimation | Relative Importance
Write Solr Technical Report | Morgan | N/A | 5 hours | **
Write Test Plan | Dominic | N/A | ? | **
Architectual Design | Morgan & Dominic | N/A | 24 hours | *****
Complete Project Plan | Morgan | N/A | 5 hours | *****
Use Case Diagram | Morgan | N/A | 2 hours | **