## Sheet1
Task/Functionality | Functional Requirement | Priority | Criticality | Time/Effort Estimation | Task | Order
Research Solr for search | - | 1 | - | 2 days | Archictecual Design | 2
Component Diagram | - | 2 | - | 3 days | Build the message store | 5
First Draft (Initial) ORM Diagrams | - | 3 | - | 5 hours | Test the message store | 6
Research SignalR for real-time message and notifications | - | 4 | - | 2 days | Project Plan | 1
Research testing plan ideas for small scrum projects | - | 5 | - | 1 day | Test Plan | 4
Add uniform formatting to documents | - | 6 | - | 1 hour | Solr Technical Report | 3
Write Test Plan |  |  |  |  | Module Registration | 7
Write Solr Report |  |  |  |  | Test Module Registration | 8
Group Messages by group | M-FR3 | 10 | Critical | TBE
Group groups by module | M-FR3 | 11 | Critical | TBE | Add dummy testing authenticaton
Any user can create a new group | M-FR4 | 8 | Critical | TBE | Notifications
Display list of groups for given module | M-FR4 | 9 | Critical | TBE | Test Notifications
Make group available to all users on the module the group belongs to | M-FR4 | 12 | Critical | TBE | Create a process for deployment
Replying to Message in group | M-FR6 |  | Critical | TBE | Front-End Server
User can edit owned message | M-FR7 |  | Critical | TBE | Test Front-End Server
Admin can delete any message | M-FR8 |  | Critical | TBE
Module staff can delete any message belonging to one of their modules | M-FR8 |  | Critical | TBE
Deleted messages are marked as deleted in database | M-FR8 |  | Critical | TBE
‘Deleted’ messages are not shown to users | M-FR8 |  | Critical | TBE
Basic Module Entity/Content | MR-FR1 |  | Critical | TBE
Admin users can create modules | MR-FR1 |  | Critical | TBE
Admin users can edit modules | MR-FR2 |  | Critical | TBE
Module has associated staff list | MR-FR1 |  | Critical | TBE
Module has associated student list | MR-FR3 |  | Critical | TBE
Module student list can be overwritten by uploaded CSV file | MR-FR3 |  | Critical | TBE
Restful Service from module registration – get modules by providing user and academic year | MR-FR4 |  | Critical | TBE
Authentication via LDAP | AA-FR1 |  | Critical | TBE
Authentication via server file for testing | AA-FR1 |  | Critical | TBE
Distinguish staff and student users by parsing return of LDAP query | AA-FR2 |  | Critical | TBE
Referring to other users in messages | M-FR2 |  | High | TBE
Students can delete an owned message if it has zero replies | M-FR8 |  | High | TBE
New message indicator for groups | M-FR9 |  | High | TBE
New message indicator for modules | M-FR9 |  | High | TBE
A user can register for notifications | N-FR1 |  | High | TBE
A user can change notification registration | N-FR1 |  | High | TBE
Internationalisation of web app | EIR-2 |  | High | TBE
Welsh language localisation | EIR-2 |  | High | TBE
Order messages inside a group by time created | M-FR3 |  | Medium | TBE
One-to-one messaging | M-FR5 |  | Medium | TBE
Order replies by time created | M-FR6 |  | Medium | TBE
Search for message by text. (Search is limited to within users’ modules) | S-FR1 |  | Medium | TBE
Add search filter within a specific module | S-FR2 |  | Medium | TBE
Add search filter within a specific group | S-FR2 |  | Medium | TBE
Add search filter within a specific academic year | S-FR2 |  | Medium | TBE
No search filter/All modules a user is associated with | S-FR2 |  | Medium | TBE
Search returns messages that match search text | S-FR3 |  | Medium | TBE
Daily Summary Notifications | N-FR2 |  | Medium | TBE
Mention Notifications | N-FR2 |  | Medium | TBE
Reply Notifications | N-FR2 |  | Medium | TBE
Notifications sent at set time intervals | N-FR3 |  | Medium | TBE
Attach emoticons to Messages | M-FR1 |  | z Low | TBE
Announcement in ‘main group’ upon new group creation | M-FR4 |  | z Low | TBE
Alert to other users when message is edited | M-FR7 |  | z Low | TBE
If search returns message of type reply the message should be expandable to show all messages in the chain of communication (both previous and future replies) | S-FR3 |  | Z Low | TBE